## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
1 | Splash Screen | Member / Authentication | Simple | Startup screen: validates the stored token and routes to Home or Login. | Iteration 1 | Done
2 | Login | Member / Authentication | Medium | Email/password and Google sign-in; wrong password and locked account handling. | Iteration 1 | Done
3 | Member Registration | Member / Authentication | Medium | Member sign-up with field validation and duplicate email check. | Iteration 1 | Done
4 | Email / OTP Verification | Member / Authentication | Medium | Verifies the email with an OTP; wrong code, expiry and resend. | Iteration 1 | Done
5 | Forgot Password | Member / Authentication | Simple | Requests a password reset link by email. | Iteration 1 | Done
6 | Reset Password | Member / Authentication | Medium | Sets a new password from the emailed link; expired link handling. | Iteration 1 | Done
7 | Change Password | Member / Authentication | Simple | Changes the password from inside the account. | Iteration 1 | Done
8 | Account Menu | Member / Profile | Simple | Entry point to wallet, consignment, orders, QR, settings, logout. | Iteration 1 | Done
9 | Member Profile | Member / Profile | Simple | Shows profile fields and the verification state. | Iteration 1 | Done
10 | Edit Profile | Member / Profile | Medium | Updates name, avatar and phone number. | Iteration 1 | Done
11 | Member QR Code | Member / Profile | Simple | Shows the QR plus a text Member code for front-desk lookup. | Iteration 1 | Doing
12 | Moderator Login (Web) | Moderator / Auth & Shell | Medium | Web sign-in; no self-registration, accounts are created by Admin. | Iteration 1 | Done
13 | Change Password (Web) | Moderator / Auth & Shell | Simple | Password change inside the settings page. | Iteration 1 | Done
14 | Application Shell | Moderator / Auth & Shell | Simple | 1440 web frame with left sidebar and header showing point name, bell and avatar. | Iteration 1 | Done
15 | Organization Registration | Organization / Authentication | Complex | Organization sign-up with legal document upload. | Iteration 1 | Done
16 | Verification Status | Organization / Authentication | Medium | Pending, rejected with reason, or verified; allows resubmission. | Iteration 1 | Done
17 | Consignment Form List | Member / Consignment | Complex | Forms grouped by status, with a warning at the 5 pending-form limit. | Iteration 1 | Done
18 | Create Consignment Form - Item | Member / Consignment | Complex | Step 1 capturing photos, brand, category, size, condition and expected price. | Iteration 1 | Done
19 | Create Consignment Form - Point | Member / Consignment | Simple | Step 2 selecting a consignment point, with nearest-point suggestion. | Iteration 1 | Done
20 | Consignment Form Details | Member / Consignment | Medium | Form detail whose CTA changes per state; rejection reason shown in full. | Iteration 1 | Done
21 | Edit Pending Form | Member / Consignment | Simple | Edits a form that is still awaiting review. | Iteration 1 | Done
22 | View Consignment Receipt | Member / Consignment | Complex | Full receipt terms showing the three commission tiers, floor price and unclaimed-goods clause. | Iteration 1 | Done
23 | Accept Consignment Receipt | Member / Consignment | Simple | Confirmation at the desk that decides whether the item is listed. | Iteration 1 | Done
24 | Consigned Item List | Member / Consignment | Complex | Consigned items grouped into lifecycle status tabs. | Iteration 1 | Done
25 | Consigned Item Details | Member / Consignment | Complex | SKU, point, price, current term, term end date, commission and expected payout. | Iteration 1 | Done
26 | Reduce Selling Price | Member / Consignment | Complex | Price reduction with floor-price, once-per-day and lower-than-current checks. | Iteration 1 | Done
27 | End-of-Term Handling | Member / Consignment | Medium | Member chooses to take the item back or re-consign; 30-day unclaimed warning. | Iteration 1 | Done
28 | Re-consign - New Price | Member / Consignment | Medium | Price re-negotiation with the moderator and a new receipt. | Iteration 1 | Done
29 | Consignment Point Dashboard | Moderator / Auth & Shell | Medium | Counters and latest tasks, all scoped to the moderator's own point. | Iteration 1 | Done
30 | Work Queue | Moderator / Work Queue | Complex | Task table across seven task types with unclaimed, mine, others and overdue filters. | Iteration 1 | Done
31 | Claim / Release Task | Moderator / Work Queue | Medium | Claim and release a task; conditional update prevents two moderators handling one case. | Iteration 1 | Done
32 | Member Lookup at Desk | Moderator / Front Desk | Complex | QR scan plus manual Member code or phone lookup. | Iteration 1 | Done
33 | Identity Confirmation | Moderator / Front Desk | Simple | Name and avatar check, mandatory before any handover. | Iteration 1 | Done
34 | Member Profile & Pending Tasks | Moderator / Front Desk | Simple | Member profile listing pending intake, pickup and end-of-term tasks. | Iteration 1 | Done
35 | Pending Consignment Forms | Moderator / Inspection & Intake | Medium | Table of forms awaiting review. | Iteration 1 | Done
36 | Form Review - Approve / Reject | Moderator / Inspection & Intake | Medium | Photo-based review with approve, reject and reason capture. | Iteration 1 | Done
37 | Start Inspection | Moderator / Inspection & Intake | Simple | Compares the submitted form against the physical item. | Iteration 1 | Done
38 | Record Inspection Result | Moderator / Inspection & Intake | Complex | Checklist and verdict covering pass, fail, counterfeit and prohibited goods. | Iteration 1 | Done
39 | Set Price & Consignment Term | Moderator / Inspection & Intake | Complex | Price agreement showing expected price, proposed price and the auto 50% floor. | Iteration 2 | Done
40 | Return Item On the Spot | Moderator / Inspection & Intake | Simple | Returns the item at the desk and records the reason. | Iteration 2 | Done
41 | Await Member Receipt Confirmation | Moderator / Inspection & Intake | Medium | Blocks stock-in until the member confirms the receipt in the app. | Iteration 2 | Done
42 | Product Entry & Stock-in | Moderator / Inspection & Intake | Complex | Full product form with photo background removal for AI try-on. | Iteration 2 | Done
43 | Quick-Add Brand | Moderator / Inspection & Intake | Simple | Short modal that adds a brand without breaking the intake flow. | Iteration 2 | Done
44 | Print SKU Label | Moderator / Inspection & Intake | Simple | Label preview and print, with reprint. | Iteration 2 | Done
45 | Re-consign - Set New Price | Moderator / Inspection & Intake | Medium | New price agreement producing a new receipt while the item stays in stock. | Iteration 2 | Done
46 | Stock List | Moderator / Stock | Complex | Stock table filtered by status and shelf location, scoped to the own point. | Iteration 2 | Done
47 | Stock Item Details | Moderator / Stock | Complex | Item detail with the full stock-in and stock-out history. | Iteration 2 | Done
48 | Scan Product QR | Moderator / Stock | Medium | QR lookup rejecting items from another point. | Iteration 2 | Done
49 | Update Shelf Location | Moderator / Stock | Simple | Short modal with an occupied-location check. | Iteration 2 | Done
50 | Unclaimed Item Handling | Moderator / Handover | Simple | Transfers unclaimed goods to a partner organization and records the evidence. | Iteration 2 | Done
51 | Categories & Brands | Moderator / Catalog | Medium | Two-tab data table; each category carries its Top/Bottom try-on slot. | Iteration 2 | Done
52 | Add / Edit Category, Brand | Moderator / Catalog | Medium | One modal for both creating and editing, with a duplicate-name check. | Iteration 2 | Done
53 | Hide Category, Brand | Moderator / Catalog | Simple | Hides instead of deleting, warning when items still use it. | Iteration 2 | Done
54 | Product Home | Member / Purchasing | Medium | Product grid and search bar; only items with status LISTED are shown. | Iteration 2 | Done
55 | Search & Results | Member / Purchasing | Medium | Keyword search with results, no-result and search history states. | Iteration 2 | Done
56 | Product Filters | Member / Purchasing | Simple | Bottom-sheet filter by category, brand, size, price and consignment point. | Iteration 2 | Done
57 | Product Details | Member / Purchasing | Medium | Item detail with images and CTA; consignor identity is never shown. | Iteration 2 | Done
58 | Shopping Cart | Member / Purchasing | Complex | Cart grouped by consignment point; unavailable items greyed out, not removed. | Iteration 2 | Done
59 | Delivery Address List | Member / Purchasing | Medium | List of saved addresses with a default flag. | Iteration 2 | Done
60 | Add / Edit Address | Member / Purchasing | Medium | One form used for both creating and editing an address. | Iteration 2 | Done
61 | Checkout | Member / Purchasing | Complex | Confirmation page; splits the order per consignment point and reserves the items. | Iteration 2 | Done
62 | MoMo Payment Result | Member / Purchasing | Complex | 15-minute countdown with success, failure, expiry and late-webhook refund states. | Iteration 2 | Done
63 | Order List | Member / Purchasing | Complex | Buyer orders grouped into status tabs. | Iteration 2 | Done
64 | Order Details | Member / Purchasing | Complex | Order timeline with six status variants and state-dependent actions. | Iteration 2 | Done
65 | Shipment Tracking | Member / Purchasing | Simple | GHN status timeline including the lost/failed shipment branch. | Iteration 2 | Done
66 | Confirm Order Receipt | Member / Purchasing | Simple | Confirmation dialog that closes the delivery step. | Iteration 2 | Done
67 | Rate Order Service | Member / Purchasing | Simple | 1-5 star rating of the order service, read-only once submitted. | Iteration 2 | Done
68 | Wallet - Balance & History | Member / Wallet | Medium | Balance header separating total and available balance, with the transaction list. | Iteration 2 | Done
69 | Transaction Details | Member / Wallet | Medium | Single wallet transaction with money-in, money-out and failed states. | Iteration 2 | Done
70 | Revenue by Order | Member / Wallet | Simple | Per-order breakdown of sale price minus commission and tax. | Iteration 2 | Done
71 | Create Payout Request | Member / Wallet | Complex | Payout form validating the 10,000d minimum, available balance and 3-per-day limit. | Iteration 2 | Done
72 | Payout Request Details | Member / Wallet | Medium | Payout status across PENDING, PROCESSING, SUCCESS and FAILED. | Iteration 2 | Done
73 | Packing Queue | Moderator / Order & Packing | Medium | Orders awaiting packing, highlighting overdue ones. | Iteration 2 | Done
74 | Order Details (Warehouse) | Moderator / Order & Packing | Complex | Warehouse order view across packing, waybill and handover states. | Iteration 2 | Done
75 | SKU Scan Check | Moderator / Order & Packing | Medium | Scan each SKU against the order checklist to prevent shipping the wrong item. | Iteration 2 | Done
76 | Create & Print GHN Waybill | Moderator / Order & Packing | Medium | Waybill preview, GHN call with retry, and tracking code display. | Iteration 2 | Done
77 | Handover at Desk | Moderator / Handover | Medium | One handover screen for withdrawal, end-of-term pickup and rejected returns. | Iteration 2 | Done
78 | Create Return Request | Member / Return | Medium | Return form requiring a reason and photos; blocked after the 3-day window. | Iteration 3 | Pending
79 | Return Request Details | Member / Return | Complex | Return timeline covering approval, handover, inspection and refund branches. | Iteration 3 | Pending
80 | Return Handover Guide | Member / Return | Simple | Instructions and waybill code for handing the parcel to GHN. | Iteration 3 | Pending
81 | Choose Rejected-Return Delivery | Member / Return | Medium | Buyer picks re-delivery at own cost or pickup at the consignment point. | Iteration 3 | Pending
82 | Create Item Withdrawal Request | Member / Consignment | Medium | Withdrawal request stating clearly whether the 7-day free window applies. | Iteration 3 | Pending
83 | Pay Withdrawal Fee | Member / Consignment | Medium | Pays the fee from the wallet, topping up through MoMo when short. | Iteration 3 | Pending
84 | Withdrawal Request Details | Member / Consignment | Medium | Request timeline with the 7-day pickup countdown and expiry. | Iteration 3 | Pending
85 | Damaged Item Handling | Member / Consignment | Medium | Member picks compensation or the item back plus partial compensation. | Iteration 3 | Pending
86 | Return Request Queue | Moderator / Return | Medium | Return requests awaiting handling, highlighting overdue ones. | Iteration 3 | Pending
87 | Return Review - Approve | Moderator / Return | Medium | Buyer photos next to order data, with approve, reject and auto-cancel branches. | Iteration 3 | Pending
88 | Inspect Returned Item | Moderator / Return | Medium | Checks the returned item against its condition at dispatch. | Iteration 3 | Pending
89 | Decide Returned-Item Outcome | Moderator / Return | Simple | Relist, return to consignor or destroy. | Iteration 3 | Pending
90 | Counterfeit Case - Second Moderator | Moderator / Return | Medium | Mandatory second opinion before any counterfeit conclusion. | Iteration 3 | Pending
91 | Counterfeit Conclusion | Moderator / Return | Simple | Refunds the buyer and destroys the item; honest consignor is not penalised. | Iteration 3 | Pending
92 | Damaged-Item Conclusion & Compensation | Moderator / Return | Medium | Records the conclusion and the compensation amount offered to the member. | Iteration 3 | Pending
93 | Lost Return Handling | Moderator / Return | Simple | Records a lost return shipment and refunds the buyer. | Iteration 3 | Pending
94 | Notifications | Member / Profile | Medium | Notification list with read/unread and empty state. | Iteration 3 | Pending
95 | Try-On Room | Member / AI Try-On | Complex | Model canvas with two slots; the item being viewed is locked into its slot. | Iteration 3 | Pending
96 | Pick Item for Empty Slot | Member / AI Try-On | Medium | Picker grid suggesting matching items for the missing slot. | Iteration 3 | Pending
97 | Generating Image | Member / AI Try-On | Medium | Progress screen for image generation with retry and background modes. | Iteration 3 | Pending
98 | Try-On Result | Member / AI Try-On | Simple | Generated outfit image with buy-single or add-whole-outfit actions. | Iteration 3 | Pending
99 | Try-On Collection | Member / AI Try-On | Simple | Grid of saved try-on images with an empty state. | Iteration 3 | Pending
100 | View & Delete Try-On Image | Member / AI Try-On | Simple | Full-screen image with a delete confirmation. | Iteration 3 | Pending
101 | Community Newsfeed | Member / Community | Medium | Feed of posts from followed organizations. | Iteration 3 | Pending
102 | Post Details | Member / Community | Medium | Post content with likes and comments. | Iteration 3 | Pending
103 | Organization Profile | Member / Community | Simple | Organization profile with campaign and post tabs, plus follow. | Iteration 3 | Pending
104 | Donation Campaign Details | Member / Community | Simple | Campaign description, period, location and accepted item types; information only. | Iteration 3 | Pending
105 | Drop-off Point Map | Member / Community | Medium | Map plus bottom-sheet list of nearby donation drop-off points. | Iteration 3 | Pending
106 | Report Violation | Member / Community | Simple | Shared reporting form for posts, campaigns and organization accounts. | Iteration 3 | Pending
107 | Conversation List | Member / Chat | Medium | Conversation list with unread markers and empty state. | Iteration 3 | Pending
108 | Chat Room | Member / Chat | Medium | One chat layout used for organizations and for the consignment-point inbox. | Iteration 3 | Pending
109 | Notifications (Web) | Moderator / Auth & Shell | Simple | Notification panel sliding from the header. | Iteration 3 | Pending
110 | Organization Dossier Queue | Moderator / Org Verification | Medium | Dossiers awaiting verification, including resubmissions. | Iteration 3 | Pending
111 | Dossier Review Checklist | Moderator / Org Verification | Complex | Eight-step checklist per organization type; the Verify button stays locked until complete. | Iteration 3 | Pending
112 | View Legal Documents | Moderator / Org Verification | Medium | Zoomable document viewer; moderator-only, download blocked, auto-deleted after 30 days. | Iteration 3 | Pending
113 | Reject Dossier with Reason | Moderator / Org Verification | Simple | Rejection modal with free text or a preset reason. | Iteration 3 | Pending
114 | Legal Info Change Queue | Moderator / Org Verification | Simple | Requests to change legal information. | Iteration 3 | Pending
115 | Review Legal Info Change | Moderator / Org Verification | Medium | Before/after comparison with the new documents attached. | Iteration 4 | Pending
116 | Violation Report Queue | Moderator / Moderation | Medium | Reports awaiting handling, grouping repeat reports on one target. | Iteration 4 | Pending
117 | Violation Report Handling | Moderator / Moderation | Complex | Removes content, hides a campaign, dismisses the report or escalates a ban to Admin. | Iteration 4 | Pending
118 | Point Inbox - Conversations | Moderator / Chat | Medium | Shared inbox for the point, visible to every moderator there. | Iteration 4 | Pending
119 | Point Inbox - Chat Room | Moderator / Chat | Simple | Chat panel with member information on the right. | Iteration 4 | Pending
120 | Organization Profile Management | Organization / Profile | Medium | Updates non-legal profile information. | Iteration 4 | Pending
121 | Request Legal Info Change | Organization / Profile | Medium | Submits a legal information change for moderator approval. | Iteration 4 | Pending
122 | Campaign List | Organization / Campaign | Medium | Own campaigns grouped by status. | Iteration 4 | Pending
123 | Create / Edit Campaign | Organization / Campaign | Complex | Campaign form with the concurrent-campaign limit enforced. | Iteration 4 | Pending
124 | Campaign Details (Owner) | Organization / Campaign | Medium | Owner view of a campaign with its drop-off points. | Iteration 4 | Pending
125 | Close / Cancel Campaign | Organization / Campaign | Simple | Closes or cancels a campaign with confirmation. | Iteration 4 | Pending
126 | Community Post List | Organization / Community | Simple | Own posts with status. | Iteration 4 | Pending
127 | Create / Edit Post | Organization / Community | Medium | Post editor with images. | Iteration 4 | Pending
128 | Delete Post | Organization / Community | Simple | Deletion with confirmation. | Iteration 4 | Pending
129 | Chat with Members | Organization / Chat | Medium | Conversations with members about campaigns. | Iteration 4 | Pending
130 | Notifications | Organization / Profile | Simple | Notification list for the organization account. | Iteration 4 | Pending
131 | Admin Dashboard | Admin / Dashboard | Complex | Revenue, orders, stock, ratings and the three platform-fund figures. | Iteration 4 | Pending
132 | Account List | Admin / Accounts | Medium | All accounts with role and status filters. | Iteration 4 | Pending
133 | Account Details | Admin / Accounts | Medium | Single account with its activity summary. | Iteration 4 | Pending
134 | Lock Account | Admin / Accounts | Simple | Locks an account and records the reason. | Iteration 4 | Pending
135 | Unlock Account | Admin / Accounts | Simple | Unlocks a previously locked account. | Iteration 4 | Pending
136 | Moderator List | Admin / Staff | Simple | Moderators with their assigned consignment point. | Iteration 4 | Pending
137 | Create Moderator Account | Admin / Staff | Medium | Creates a moderator account; no self-registration exists. | Iteration 4 | Pending
138 | Assign Moderator to Point | Admin / Staff | Simple | Assigns or moves a moderator between points. | Iteration 4 | Pending
139 | Consignment Point List | Admin / Points | Simple | All consignment points with status. | Iteration 4 | Pending
140 | Create Consignment Point | Admin / Points | Medium | Creates a point with address and coordinates. | Iteration 4 | Pending
141 | Edit Consignment Point | Admin / Points | Medium | Edits point information. | Iteration 4 | Pending
142 | Hide Consignment Point | Admin / Points | Simple | Hiding is blocked while stock remains at the point. | Iteration 4 | Pending
143 | System Parameter List | Admin / Configuration | Complex | All parameters from the configuration table: terms, commission, floor price, fees, limits. | Iteration 4 | Pending
144 | Edit System Parameter | Admin / Configuration | Medium | Edits a parameter; every change is written to the audit log. | Iteration 4 | Pending
145 | Revenue & Order Report | Admin / Reports | Complex | Revenue and order figures by period. | Iteration 4 | Pending
146 | Inventory & Rating Report | Admin / Reports | Medium | Stock levels and service ratings by point. | Iteration 4 | Pending
147 | Platform Fund Overview | Admin / Reports | Complex | Platform fund balance against member wallet liabilities. | Iteration 4 | Pending
148 | Export Excel Report | Admin / Reports | Simple | Exports the current report to Excel. | Iteration 4 | Pending
149 | Audit Log List | Admin / Audit | Medium | Audit entries filtered by actor, object and period. | Iteration 4 | Pending
150 | Audit Log Details | Admin / Audit | Medium | Single audit entry with before and after values. | Iteration 4 | Pending
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple | <=7 fields | <=3 transactions
| medium | <=15 fields | <= 7 transactions
| complex | >15 fields | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)