CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Ho Chi Minh City, September 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 18/10/2026 | M | NganNNK | 6. Configuration Management |
| 27/10/2026 | M | NganNNK | II. 1.1 Scope & Estimation: Updated WBS items, feature scope, complexity classifications, and estimated efforts to align with revised ReHome business requirements. |
| 27/10/2026 | M | NganNNK | II. 1.2 Project Objectives: Updated critical business-flow coverage and clarified testing criteria. |
| 27/10/2026 | M | NganNNK | II. 1.3 Project Risks: Updated third-party integration risks and added wallet and financial-ledger consistency risks. |
| 27/10/2026 | M | NganNNK | II. 2.3 Training Plan: Aligned AI Virtual Try-On training scope with the selected technical approach. |
| 27/10/2026 | M | NganNNK | II. 3. Project Deliverables: Clarified delivery milestones and deployment scope. |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Initiation (Stage 1) |  | 12 |
| 1.1 | Define project scope & context | Medium | 2 |
| 1.2 | Define objectives, target users, functional / non-functional requirements | Medium | 3 |
| 1.3 | Research existing solutions (resale platforms, donation platforms, virtual try-on) | Medium | 3 |
| 1.4 | Prepare & deliver Report 1 (Project Introduction) | Simple | 2 |
| 1.5 | Review with supervisor & revise | Simple | 2 |
| 2 | Planning & Requirement (Stage 2) |  | 26 |
| 2.1 | Prepare Project Management Plan (Report 2) | Medium | 4 |
| 2.2 | Set up repository, CI, coding convention, environments | Medium | 3 |
| 2.3 | Prototype AI Try-On, MoMo, VNPay and GHN Sandbox integrations | Complex | 7 |
| 2.4 | Requirement analysis & write SRS | Complex | 10 |
| 2.5 | Review SRS & Plan with supervisor | Simple | 2 |
| 3 | Software Designing (Stage 3) |  | 28 |
| 3.1 | Software Design Document (architecture, class & sequence diagrams) | Complex | 10 |
| 3.2 | UI/UX design prototype (Web + Mobile) | Complex | 10 |
| 3.3 | Database design (PostgreSQL) | Complex | 6 |
| 3.4 | Review SDS with supervisor | Simple | 2 |
| 4 | Implementation (Stage 4) |  | 189 |
| 4.1 | Code Iteration 1 — Foundation, Account & Consignment |  | 68 |
| 4.1.1 | Update SRS & SDS (Iteration 1) | Medium | 2 |
| 4.1.2 | Create test cases (Iteration 1) | Complex | 4 |
| 4.1.3 | Feature development (Iteration 1) |  | 62 |
| 4.1.3.1 | Project Foundation & Common Services |  | 12 |
| 4.1.3.1.1 | Set up layered architecture & project skeleton (Spring Boot, ReactJS, React Native) | Complex | 3 |
| 4.1.3.1.2 | Design database schema for accounts, inventory, wallets and financial ledger | Complex | 4 |
| 4.1.3.1.3 | JWT authentication, role-based authorization, Google OAuth 2.0 | Complex | 3 |
| 4.1.3.1.4 | Image storage & CDN integration (Cloudinary) | Medium | 2 |
| 4.1.3.2 | Account & Common Access |  | 11 |
| 4.1.3.2.1 | Register Member account; register Organization account with legal documents | Complex | 2 |
| 4.1.3.2.2 | Login by password / Google, route organization by verification status, logout | Medium | 2 |
| 4.1.3.2.3 | Reset forgotten password, change password | Medium | 1 |
| 4.1.3.2.4 | Resubmit rejected organization profile | Simple | 1 |
| 4.1.3.2.5 | View, update personal profile | Simple | 1 |
| 4.1.3.2.6 | Display the Member code for identification at warehouse counters | Medium | 1 |
| 4.1.3.2.7 | View products; search and filter products by category, brand, price, size, condition | Medium | 3 |
| 4.1.3.3 | Consignment — Member (Seller) |  | 18 |
| 4.1.3.3.1 | Submit consignment form, suggest nearest warehouse, limit pending forms | Complex | 3 |
| 4.1.3.3.2 | Edit pending form, view consignment forms, expire approved form | Medium | 2 |
| 4.1.3.3.3 | Manage digital consignment receipt and PDF generation | Complex | 3 |
| 4.1.3.3.4 | View consigned products, reduce selling price | Simple | 1 |
| 4.1.3.3.5 | Manage consignment renewals, deadlines and free-withdrawal windows | Complex | 2 |
| 4.1.3.3.6 | Process item withdrawals and Wallet/MoMo/VNPay fee payments | Complex | 2 |
| 4.1.3.3.7 | Close item withdrawal requests after handover; automatically expire uncollected withdrawal requests and restore eligible items to sale. | Medium | 2 |
| 4.1.3.3.8 | Handle end-of-term reclamation and re-consignment | Complex | 3 |
| 4.1.3.4 | Moderator — Consignment Review & Counter Intake |  | 21 |
| 4.1.3.4.1 | Look up Members by Member code or phone number; open Member profiles and pending tasks | Medium | 2 |
| 4.1.3.4.2 | View work queues, claim task, auto-release claimed task after 48h | Complex | 3 |
| 4.1.3.4.3 | Review consignment form of the assigned warehouse | Complex | 3 |
| 4.1.3.4.4 | Start item inspection; verify the Member at the counter using the account name and avatar. | Medium | 2 |
| 4.1.3.4.5 | Record inspection result & final price, return item on the spot | Complex | 3 |
| 4.1.3.4.6 | Enter product info and stock in, quick-add brand | Complex | 3 |
| 4.1.3.4.7 | Process try-on photo via background-removal API | Complex | 3 |
| 4.1.3.4.8 | Confirm unclaimed consignment items and record inventory disposition and handover to partner charities. | Medium | 2 |
| 4.2 | Code Iteration 2 — Purchasing, Payment, Fulfilment & Seller Revenue |  | 63 |
| 4.2.1 | Update SRS & SDS (Iteration 2) | Medium | 2 |
| 4.2.2 | Create test cases (Iteration 2) | Complex | 4 |
| 4.2.3 | Feature development (Iteration 2) |  | 57 |
| 4.2.3.1 | Purchasing — Member (Buyer) |  | 25 |
| 4.2.3.1.1 | Manage shopping cart: add, view, remove product | Medium | 2 |
| 4.2.3.1.2 | Manage shipping address: view, create, edit, delete | Simple | 1 |
| 4.2.3.1.3 | Place order, split order per warehouse, calculate shipping fee | Complex | 4 |
| 4.2.3.1.4 | Process order payments via Wallet/MoMo/ VNPay | Complex | 5 |
| 4.2.3.1.5 | Automatically cancel unpaid orders after the payment deadline; handle delivery failures or lost parcels reported by GHN and trigger eligible wallet refunds. | Medium | 2 |
| 4.2.3.1.6 | View orders and track delivery status; allow cancellation of paid orders only before packing and trigger a full refund to the buyer's ReHome wallet. | Medium | 3 |
| 4.2.3.1.7 | Complete orders and credit seller earnings to wallets | Complex | 3 |
| 4.2.3.1.8 | Rate order service per warehouse | Simple | 1 |
| 4.2.3.1.9 | Submit return request, hand returned goods to GHN, cancel return on missed handover | Complex | 3 |
| 4.2.3.1.10 | Choose handling of invalid return, expire invalid-return pickup | Medium | 1 |
| 4.2.3.2 | Moderator — Warehouse Fulfilment & Return Handling |  | 14 |
| 4.2.3.2.1 | Print SKU label, scan product QR, update shelf location | Medium | 2 |
| 4.2.3.2.2 | View warehouse inventory, record stock movement | Complex | 2 |
| 4.2.3.2.3 | Pack and ship order, sync GHN shipment status | Complex | 3 |
| 4.2.3.2.4 | Verify withdrawal fee payment and hand over items at the warehouse counter. | Medium | 2 |
| 4.2.3.2.5 | Review return requests, inspect returned goods, determine return validity and product disposition, and identify degraded items requiring compensation. | Complex | 3 |
| 4.2.3.2.6 | Enforce second-Moderator verification for suspected counterfeit returns and record the final decision. | Medium | 2 |
| 4.2.3.3 | Member Wallet, Revenue & Automated Payout |  | 18 |
| 4.2.3.3.1 | View Member wallet balance, available balance, and transaction history | Medium | 2 |
| 4.2.3.3.2 | View seller earnings by completed order and wallet credit | Medium | 1 |
| 4.2.3.3.3 | Submit wallet withdrawal requests and validate available balance and configured limits | Complex | 2 |
| 4.2.3.3.4 | Process simulated payouts and manage locked balances | Complex | 2 |
| 4.2.3.3.5 | Implement platform fund and double-entry ledger | Complex | 4 |
| 4.2.3.3.6 | Process wallet refunds and reconcile transactions | Complex | 4 |
| 4.2.3.3.7 | Calculate and credit degraded-item compensation | Complex | 3 |
| 4.3 | Code Iteration 3 — Virtual Try-On, Donation, Organization & Admin |  | 58 |
| 4.3.1 | Update SRS & SDS (Iteration 3) | Medium | 2 |
| 4.3.2 | Create test cases (Iteration 3) | Complex | 3 |
| 4.3.3 | Feature development (Iteration 3) |  | 53 |
| 4.3.3.1 | AI Virtual Try-On & Try-On Collection |  | 13 |
| 4.3.3.1.1 | Open AI Virtual Try-On from the product detail page and assign the selected product to its corresponding Top or Bottom slot | Medium | 2 |
| 4.3.3.1.2 | Select a male or female model for the try-on session | Simple | 1 |
| 4.3.3.1.3 | Suggest a complementary product for the missing clothing slot | Simple | 1 |
| 4.3.3.1.4 | Allow manual selection of the complementary product and validate both mandatory Top and Bottom slots | Medium | 1 |
| 4.3.3.1.5 | Validate product availability when adding try-on products to the shopping cart | Medium | 2 |
| 4.3.3.1.6 | Handle try-on image generation requests, loading states, timeouts, and errors | Complex | 2 |
| 4.3.3.1.7 | Integrate the self-hosted AI image-generation model using prepared product photographs | Complex | 3 |
| 4.3.3.1.8 | Save, view, and delete generated images in the personal try-on collection | Simple | 1 |
| 4.3.3.2 | Donation & Community — Member |  | 4 |
| 4.3.3.2.1 | View organization profile, view donation campaigns | Simple | 1 |
| 4.3.3.2.2 | View nearby organizations & campaign locations on map | Medium | 1 |
| 4.3.3.2.3 | Follow organization, view community posts, like and comment post | Simple | 1 |
| 4.3.3.2.4 | Report violation | Simple | 1 |
| 4.3.3.3 | Organization Mobile — Campaign & Community Management |  | 9 |
| 4.3.3.3.1 | Update basic profile, request legal information change | Medium | 2 |
| 4.3.3.3.2 | Create, edit, and manually close informational donation campaigns; configure receiving periods, locations, preferred clothing types, and enforce the limit on concurrent active campaigns. | Complex | 4 |
| 4.3.3.3.3 | Automatically close donation campaigns when their receiving period ends; display campaign status and details without tracking donated quantities or weights. | Medium | 2 |
| 4.3.3.3.4 | Create, edit, delete, view own community posts | Medium | 1 |
| 4.3.3.4 | Chat & Notification |  | 7 |
| 4.3.3.4.1 | Real-time chat between Member and Organization | Complex | 2 |
| 4.3.3.4.2 | Chat with warehouse inbox, Moderator answers warehouse inbox | Complex | 2 |
| 4.3.3.4.3 | In-app & email notification for Member, Organization, Moderator | Complex | 2 |
| 4.3.3.4.4 | Notify Admin of overdue tasks | Simple | 1 |
| 4.3.3.5 | Moderator — System-wide Tasks |  | 7 |
| 4.3.3.5.1 | Verify organization registration, approve or reject organization | Complex | 2 |
| 4.3.3.5.2 | Restrict access & auto-delete legal documents | Medium | 1 |
| 4.3.3.5.3 | Review legal information change request | Medium | 1 |
| 4.3.3.5.4 | Handle violation report | Medium | 2 |
| 4.3.3.5.5 | Manage category and brand: view, create, edit, hide | Medium | 1 |
| 4.3.3.6 | Admin Management & System Settings |  | 13 |
| 4.3.3.6.1 | View accounts, ban account, unban account | Medium | 2 |
| 4.3.3.6.2 | Create, update Moderator account, assign Moderator to warehouse | Medium | 2 |
| 4.3.3.6.3 | Manage warehouse: view, create, edit, hide | Medium | 2 |
| 4.3.3.6.4 | Manage configurable business parameters | Complex | 2 |
| 4.3.3.6.5 | Display operational and financial dashboards | Complex | 3 |
| 4.3.3.6.6 | Export Admin Dashboard data, including platform revenue and financial summaries, to Excel. | Medium | 1 |
| 4.3.3.6.7 | View audit logs and record Moderator actions, financial transactions, system configuration changes, and other auditable administrative activities. | Medium | 1 |
| 5 | Verification (Stage 5) |  | 24 |
| 5.1 | Execute end-to-end tests and resolve defects | Complex | 12 |
| 5.2 | Prepare for deployment (Docker, Railway, environment configuration) | Medium | 7 |
| 5.3 | Update project documents (Report 5 – Testing Documentation) | Medium | 5 |
| 6 | Transition (Stage 6) |  | 21 |
| 6.1 | Optimize / refactor code | Medium | 4 |
| 6.2 | Conduct sandbox-based UAT and resolve defects | Medium | 4 |
| 6.3 | Deploy final code | Medium | 3 |
| 6.4 | Prepare User Guide document (Report 6) | Simple | 4 |
| 6.5 | Prepare Final Project Report (Report 7) | Complex | 4 |
| 6.6 | Prepare thesis presentation & demo script | Simple | 2 |
|  | Total Estimated Effort (man-days) |  | 300 |

##### Table 1. Scope and Estimation

- Milestone Timeliness (%): The project must be finished before (20 December 2026)

- Allocated Effort (man-days): 4 (members) * 15(weeks) * 7(days/weeks) = 420 man-days

### 1.2 Project Objectives

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | 100% of SRS/SDS/code documents reviewed | Target: 0 Critical/High finding | ≤ 5% |  |
| 2 | Unit Test | ≥ 70% code coverage (core business logic) | Target: 0 Critical/High defect | ≤ 5% |  |
| 3 | Integration Test | ≥ 90% module integration covered | Target: 0 Critical/High defect | ≤ 5% |  |
| 4 | System Test | 100% critical business flows covered, including consignment lifecycle, Wallet/MoMo/ VNPay payments, order fulfilment, returns and refunds, simulated payouts, AI Virtual Try-On, informational donation campaigns, and system administration. | Target: 0 Critical/High defect | ≤ 5% |  |
| 5 | Acceptance Test | 100% Must-have use case | Target: 0 Critical/High defect | 0% |  |

##### Table 2. Project Objectives

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Conflicts between team members | Medium | Medium | Hold regular team meetings to discuss and resolve disagreements early |
| 2 | Proposed solution may not match real user needs | High | Medium | Study existing platforms and validate requirements with mentor before finalizing |
| 3 | Team lacks experience with some required technologies | Medium | Low | Set aside time early for self-study and small technical trials |
| 4 | Sensitive user data (accounts, wallet, payment) could be exposed or misused | High | Medium | Encrypt sensitive data, restrict access by role, and review code before release |
| 5 | Project deadline may be too tight for the planned scope | Medium | Medium | Prioritize core features first, split work evenly, and adjust the plan early if falling behind |
| 6 | Requirements keep changing after the SRS is approved (scope creep) | High | Medium | Freeze the baseline after Report 3; every change must go through the Record of Changes and be approved by the supervisor; assess the effort impact before accepting |
| 7 | Dependency on third-party services (MoMo, VNPay, GHN, background-removal API, cloud storage, map service): quota limit, API change or downtime | High | Medium | Access every external service through an interface/adapter so it can be swapped; use sandbox keys during development; log and retry failed calls |
| 8 | Wallet or platform ledger inconsistencies caused by duplicate payment webhooks, concurrent transactions, or failed refunds and payouts | High | Medium | Implement idempotent payment processing, transactional wallet updates, balance locking, ledger reconciliation, and automated tests for duplicate and failed transactions. |

##### Table 3. Project Risks

## 2. Management Approach

### 2.1 Project Process

Our software development lifecycle methodology is Scrum, which is an iterative and flexible framework for developing, delivering, and maintaining products. Scrum emphasizes adaptability, collaboration, and continuous delivery of value to ensure that the product can evolve alongside changing requirements and user needs. The reasons for adopting Agile in our project include:

- Iteration planning: This allows the team to break down the project into smaller, manageable tasks, prioritize them effectively, and set clear goals for each sprint. It helps ensure that the most important features are always being worked on first.

- Daily Stand-ups: These short meetings keep everyone aligned, encourage collaboration, and help quickly identify any blockers. By maintaining constant communication, the team can adapt and resolve issues before they grow into bigger problems.

- Sprint reviews and demo: At the end of each sprint, the team showcases the completed work to stakeholders. This not only provides transparency but also invites early feedback, making it easier to adjust direction if needed and ensuring the product evolves in line with expectations.

This iterative approach enables rapid response to changes and continuous improvement while keeping the project on track.

### 2.2 Quality Management

To maintain the quality of the Pre-Owned Clothing platform, the team applies quality-control activities throughout the development process. These activities focus on preventing defects early, reviewing work regularly, and testing the system at different levels.

- Defect Prevention:
Before development begins, the team clarifies requirements and follows agreed coding conventions. Clear documentation and knowledge-sharing sessions are maintained to reduce misunderstandings and prevent common errors.

- Reviewing:
Requirements, designs, and source code are reviewed during development. Team members provide feedback through both informal discussions and code reviews, while sprint retrospectives are used to identify improvements for subsequent sprints.

- Unit and Integration Testing:
Developers test individual functions and business-logic components while implementing features. Where appropriate, tests are developed alongside the code to verify expected behaviour early. After unit testing, integration testing is performed to ensure that the frontend, backend APIs, and database work correctly together as new features are integrated.

- System Testing:
At the end of each sprint, the team performs end-to-end testing based on realistic user scenarios. This confirms that completed features operate correctly within the overall system and satisfy the agreed user requirements.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Spring Boot | TaiTNA, NguyenNM | 28/09/2026 (2 weeks) | Mandatory |
| PostgreSQL & Redis | TaiTNA, NguyenNM | 28/09/2026 (1 week) | Mandatory |
| ReactJS | NganNNK | 28/09/2026 (2 weeks) | Mandatory |
| React Native | HanhTTM | 28/09/2026 (2 weeks) | Mandatory |
| Git, GitHub Workflow & Scrum with Jira | All team members | 28/09/2026 (4 days) | Mandatory |
| JWT Authentication & Google OAuth 2.0 Integration | TaiTNA | 05/10/2026 (5 days) | Mandatory |
| Cloudinary & Background Removal API Integration for Product Photos | NguyenNM | 12/10/2026 (5 days) | Mandatory |
| MoMo/ VNPay Sandbox Payment Integration | TaiTNA | 19/10/2026 (6 days) | Mandatory |
| GHN Integration for Freight Shipping | TaiTNA | 26/10/2026 (5 days) | Mandatory |
| AI Virtual Try-On (self-hosted pre-trained model; optional LoRA fine-tuning evaluation) | NguyenNM | 02/11/2026 (2 weeks) | Mandatory |
| WebSocket / STOMP Integration for Real-time Messaging | TaiTNA | 09/11/2026 (4 days) | Mandatory |
| Google Maps Integration for Location Display | HanhTTM | 13/11/2026 (3 days) | Mandatory |
| Docker & Railway Deployment | TaiTNA | 16/11/2026 (5 days) | Mandatory |
| JUnit 5, Mockito & Postman for Testing | TaiTNA, NguyenNM | 23/11/2026 (4 days) | Mandatory |

##### Table 6. Training Plan

## 3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Project Introduction (Report 1) | 11/09/2026 | Project Introduction Document |
| 2 | Project Management Plan (Report 2) | 18/09/2026 | Project Management Plan Document |
| 3 | Software Requirement Specification (Report 3) | 25/09/2026 | Context Diagram, Use case diagram, ... |
| 4 | Software Design Documentation (Report 4) | 25/09/2026 | System architecture, class diagram, sequence diagram, …. |
| 5 | Software Testing Documentation (Report 5) | 06/11/2026 | Test strategy, test plan, test case, ... |
| 6 | Software User Guides (Report 6) | 27/11/2026 | Installation guides, user manual guides, ... |
| 7 | Final Report (Report 7) | 04/12/2026 | Include all project documentations |
| 8 | Code Package Back-end | 06/11/2026 | Code & Unit Test, Integration Test |
| 10 | Code Package Mobile | 04/12/2026 | Code |
| 9 | Code Package Front-end | 04/12/2026 | Code |
| 11 | Deployed System | 04/11/2026 | Backend on Railway, web Vercel, Mobile build for demo. |
| 12 | Final presentation slides | 27/11/2026 | Slide file |

## 4. Responsibility Assignments

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | TaiTNA | NguyenNM | NganNNK | HanhTTM |
| --- | --- | --- | --- | --- |
| Project Introduction (Report 1) | R | D | S | S |
| Project Management Plan (Report 2) | S | S | D | R |
| Software Requirement Specification (Report 3) | D | R | R | R |
| Software Design Documentation (Report 4) | D | R | S | S |
| Software Testing Documentation (Report 5) | R | D | S | S |
| Software User Guides (Report 6) | R | S | S | D |
| Final Report (Report 7) | D | S | S | S |
| Code Package Back-end | D | D | I | I |
| Code Package Front-end | I | I | D | I |
| Code Package Mobile | I | I | I | D |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Supervisor (Lecturer) | Mr. Nguyen Xuan Huy Mr. Nguyen Trong Tai | - Provide document template - Instruct the project team - Review deliverables - Supervise project status - Receive report project | Weekly | Face-to-face meeting Zalo |
| Meeting | Team members | - Collaborate on mutual task - Planning | Weekly | Google Meets, Discord, Zalo |
| Messages | Team members | - Share daily progress made on project tasks - Share current and potential roadblocks | Daily | Zalo, Discord |
| Sprint Planning | Team members | - Select backlog items for the sprint - Estimate and assign tasks | Every 2 weeks (start of sprint) | Google Meet, Jira |
| Sprint Review & Retrospective | Team members, Supervisor | - Demo the sprint result - Collect feedback - Identify improvements for the next sprint | Every 2 weeks (end of sprint) | Face-to-face meeting, Google Meet |
| Daily Stand-up | Team members | - Share yesterday / today plan - Raise blockers early | Daily (15 minutes) | Discord, Zalo |

## 6. Configuration Management

### 6.1 Document Management

- Document tools: Google Docs, Google Sheets

- File Management: Google Drive

### 6.2 Source Code Management

- Our team uses GitHub to manage the source code version

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | ReactJS (Web Frontend), React Native (Mobile App), Spring Boot (Backend) |
| Database | PostgreSQL, Redis |
| Cloud Services | Cloudinary, MoMo, VNPay, GHN, Google OAuth 2.0, Google Maps, SMTP mail service, third-party background-removal API |
| IDEs/Editors | Visual Studio Code, IntelliJ IDEA, Android Studio |
| Diagramming | DrawIO, Visual Paradigm, Mermaid Chart |
| Documentation | Google Docs/Sheets/Slides |
| Version Control | GitHub (Source Codes), Google Drive (Documents) |
| Deployment server | Railway (Backend Hosting), Docker (Containerization) |
| Project management | Google Sheet, Jira, Github Project |
| Testing | JUnit 5, Mockito, JaCoCo, Swagger |
| CI/CD | GitHub Actions |